## RiskAssessment
ID | Asset | Threat | Vulnerability | Likelihood | Impact | RawRisk | ExistingControls | ControlsEffectiveness | ResidualRisk | RecommendedAction | Priority | Status | Owner | TargetDate | Notes
1 | POS System / Email | Unauthorized Access | Shared staff accounts | 3 - Likely | 3 - High |  | None | 0 |  | Create separate user accounts for staff |  | Not Started | owner |  | Example
2 | POS System | Ransomware | Outdated software | 3 - Likely | 4 - Critical |  | Basic AV | 0.1 |  | Patch POS; backups | High | Not Started | IT Support
3 | Wi-Fi Network | Unauthorized Access | Default password | 3 - Likely | 3 - High |  | Single Wi-Fi | 0.15 |  | Change router creds; guest VLAN | Medium | Not Started | Owner
4 | Banking Portal / Email | Phishing Attack | Staff unaware of phishing risks | 4 – Very Likely | 3 – High |  | Basic spam filter | 0.15 |  | Conduct phishing awareness training | High | Not Started | HR / IT
5 | POS System | Malware Infection | No endpoint protection on POS | 3 – Likely | 4 – Critical |  | Limited antivirus | 0.1 |  | Deploy enterprise-grade antivirus on POS terminals | High | In Progress | IT Support
6 | CCTV / Security System | Physical Tampering | No password protection on CCTV DVR | 3 – Likely | 3 – High |  | Default configuration | 0.2 |  | Set strong passwords; restrict physical access | Medium | Not Started | Security
7 | Wi-Fi Network / POS | Data Interception | Unencrypted data transmission | 4 – Very Likely | 4 – Critical |  | WPA2 only | 0.1 |  | Upgrade to WPA3; use VPN for POS traffic | High | Not Started | Network Admin
8 | Staff Laptops | Data Loss / Theft | No device encryption or backup policy | 3 – Likely | 4 – Critical |  | Password-only protection | 0.1 |  | Implement encryption and cloud backup policy | High | Planned | IT Admin
9 | Email / Admin Panel | Privilege Escalation | Excessive admin rights granted | 3 – Likely | 4 – Critical |  | Limited audit logs | 0.1 |  | Implement role-based access control (RBAC) | High | Not Started | System Admin
10 | Backup Drive / Cloud | Ransomware / Data Corruption | No offline/offsite backups | 3 – Likely | 4 – Critical |  | Weekly local backup | 0.15 |  | Adopt 3-2-1 backup strategy with offsite storage | High | Planned | IT Support